## Curriculum
Sl No | Assignment | Assignment Details | Assigned Date | Duration | Expected Completion Date | Snehitha Gulla |  | Shabana Sheik |  | Hariprasad Mallipudi |  | Shankar Buddha |  | Narasinga Koppu |  | Prasad Balaga |  | Santosh Mudiganti |  | Kartheek Yandava
[6 empty] | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date
1 | Beginner: Introduction to Generative AI ¦ Google Skills | Introduction to Generative AI | 2025-11-17 | 45 minutes | 2025-11-21 | Complete |  | Complete |  | Complete | 2025-11-18 | Complete | 18-11-2025 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete
2 | https://www.cloudskillsboost.google/paths/118 | Introduction to Large Language Models | 2025-11-17 | 1 hour | 2025-11-21 | Complete |  | Complete |  | Complete | 2025-11-18 | Complete | 18-11-2025 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete
3 | https://www.cloudskillsboost.google/paths/118 | Introduction to Responsible AI | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete |  | Complete | 2025-11-18 | Complete | 18-11-2025 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete | 2025-11-17 | Complete
4 | https://www.cloudskillsboost.google/paths/118 | Prompt Design in Vertex AI | 2025-11-17 | 3 hours 45 minutes | 2025-11-21 | Complete |  | Complete | 2025-11-18 | Complete | 2025-11-18 | Complete | 19-11-2025 | Complete | 2025-11-18 | On-Hold | Unable to complete lab as content not loading | Complete | 2025-12-02 | Complete
5 | https://www.cloudskillsboost.google/paths/118 | Responsible AI: Applying AI Principles with Google Cloud | 2025-11-17 | 2 hours | 2025-11-21 | Complete |  | Complete |  | Complete | 2025-11-18 | Complete | 19-11-2025 | Complete | 2025-11-20 | Complete | 2025-11-18 | Complete | 2025-11-17 | Complete
6 | https://www.simplilearn.com/prompt-engineering-free-course-skillup?form=MG0AV3 | Introduction to Prompt Engineering Fundamentals | 2025-11-17 | 1 Hour | 2025-11-21 | Complete |  | Complete | https://certificates.simplicdn.net/share/7603660_78224861732710453259.pdf | Complete | 2025-11-18 | Complete | 19-11-2025 | Complete | 2025-11-24 | Complete | 2025-11-19 | Complete | 2025-12-02 | Complete
7 | https://machinelearningmastery.com/prompt-engineering-for-effective-interaction-with-chatgpt/?_gl=1*awltxd*_gcl_au*MTE0NzgyNTU0MC4xNzMxMzI1MTIz*_ga*MjkyMDA0NTE5LjE3MzEzMjUxMjM.*_ga_67L1RV734X*MTczMTMyNTEyMi4xLjEuMTczMTMyNTE1MS4zMS4wLjE5MzQzODg0Mzg%2E | Prompt Engineering for Effective Interaction with ChatGPT | 2025-11-17 |  | 2025-11-21 | Complete |  | Complete |  | Complete | 2025-11-18 | Complete | 20-11-2025 | Complete | 2025-11-24 | Complete | 2025-11-19 | Complete | 2025-12-02 | Complete
8 | https://www.cloudskillsboost.google/paths/183 | Introduction to Image Generation | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete | https://drive.google.com/file/d/1praXmhLzu47dNWFTZEeDD3Ult3CqYlrj/view?usp=drive_link | Complete | 2025-11-21 | Complete | 20-11-2025 | Complete | 2025-11-24 | Complete | 2025-11-20 | Complete | 2025-12-02 | Complete
9 | https://www.cloudskillsboost.google/paths/183 | Attention Mechanism | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete | https://drive.google.com/file/d/1xPjp_rOHpJPwHMlX5_TrrhAbPhCPy9Ez/view?usp=drive_link | Complete | 2025-11-21 | Complete | 20-11-2025 | Complete | 2025-11-24 | Complete | 2025-11-20 | Complete | 2025-12-02 | Complete
10 | https://www.cloudskillsboost.google/paths/183 | Encoder-Decoder Architecture | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete | 2026-01-06 | Complete | 2025-11-21 | Complete | 16-12-2025 | Complete | 2025-11-26 | Complete | 2025-11-20 | Complete | 2025-12-02 | Complete
11 | https://www.cloudskillsboost.google/paths/183 | Transformer Models and BERT Model | 2025-11-17 | 2 hours | 2025-11-21 | Complete |  | Complete | 2026-01-06 | Complete | 2025-11-28 | Complete | 17-12-2025 | Complete | 2025-11-27 | Complete |  | Complete | 2025-12-02 | Complete
12 | https://www.cloudskillsboost.google/paths/183 | Create Image Captioning Models | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete | 2026-01-06 | Complete | 2025-11-28 | Complete | 18-12-2025 | Complete | 2025-11-28 | Complete |  | Complete | 2025-12-02 | Complete
13 | https://www.cloudskillsboost.google/paths/183 | Introduction to Vertex AI Studio | 2025-11-17 | 2 hours | 2025-11-21 | Complete |  | Complete | 2026-01-07 | Complete | 2026-01-05 | Complete | 19-12-2025 | Complete | 2025-11-29 | Complete |  | Complete | 2025-12-02 | Complete
14 | https://www.cloudskillsboost.google/paths/183 | Vector Search and Embeddings | 2025-11-17 | 2 hours | 2025-11-21 | On-Hold | Challenge in launching the lab due to credit limitations | Complete | 2026-01-09 | On-Hold | Challenge in launching the lab due to credit limitations | On-Hold | 22-12-2025 | On-Hold | credit limitations | On-Hold | Unable to complete lab as content not loading | On-Hold | Unable to complete | On-Hold
15 | https://www.cloudskillsboost.google/paths/183 | Inspect Rich Documents with Gemini Multimodality and Multimodal RAG | 2025-11-17 | 4 hours 45 minutes | 2025-11-21 | On-Hold | No Credits | On-Hold | one lab is left to complete in this course due to limited credits. | On-Hold | Challenge in launching the lab due to credit limitations | On-Hold | 23-12-2025 | On-Hold | credit limitations | Complete |  | On-Hold | Unable to complete | In-Progress
16 | https://www.cloudskillsboost.google/paths/183 | Responsible AI for Developers: Fairness & Bias | 2025-11-17 | 4 hours | 2025-11-21 | On-Hold | No Credits | On-Hold | No credits | On-Hold | Challenge in launching the lab due to credit limitations | On-Hold | 26-12-2025 | On-Hold | credit limitations | Complete |  | On-Hold | Unable to complete | Complete
17 | https://www.cloudskillsboost.google/paths/183 | Responsible AI for Developers: Interpretability & Transparency | 2025-11-17 | 3 hours | 2025-11-21 | On-Hold | No Credits | On-Hold | No credits | On-Hold | Challenge in launching the lab due to credit limitations | On-Hold | 29-12-2025 | On-Hold | credit limitations | Complete |  | On-Hold | Unable to complete | Complete
18 | https://www.cloudskillsboost.google/paths/183 | Responsible AI for Developers: Privacy & Safety | 2025-11-17 | 5 hours | 2025-11-21 | On-Hold | No Credits | On-Hold | No credits | On-Hold | Challenge in launching the lab due to credit limitations | On-Hold | 30-12-2025 | On-Hold | credit limitations | Complete |  | On-Hold | Unable to complete | Complete
19 | https://www.cloudskillsboost.google/paths/183 | Machine Learning Operations (MLOps) for Generative AI | 2025-11-17 | 30 minutes | 2025-11-21 | Complete |  | Complete | 2026-01-07 | Complete | 2026-01-05 | Complete | 2026-01-05 | Complete | 2025-12-22 | Complete |  | On-Hold | Unable to complete | Complete
20 | https://drive.google.com/file/d/12vWnFmbM3jRuiCTXkL_Sy93BUOEalChV/view | GitHub CoPilot training video | 2025-11-17 | 1 hour | 2025-11-21 | Open |  | Complete | 2026-01-09 | Complete | 2026-01-06 | Complete | 2026-01-05 | Complete | 2025-12-22 | Complete |  | Complete | 2025-12-02 | Complete
21 | https://github.com/features/copilot/tutorials | Get started in Visual Studio Code - Lesson 1: GitHub Copilot 101 | 2025-11-17 | 5 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-05 | Complete | 2025-12-23 | Complete |  | Complete | 2025-12-02 | Complete
22 | https://github.com/features/copilot/tutorials | Get started in Visual Studio Code - Lesson 2: Mastering the basics | 2025-11-17 | 7 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-06 | Complete | 2025-12-23 | Complete |  | Complete | 2025-12-02 | Complete
23 | https://github.com/features/copilot/tutorials | Get started in Visual Studio Code - Lesson 2: Mastering the basics | 2025-11-17 | 9 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-06 | Complete | 2025-12-24 | Complete |  | Complete | 2025-12-02 | Open
24 | https://github.com/features/copilot/tutorials | Get started in Visual Studio -Lesson 1: GitHub Copilot 101 | 2025-11-17 | 16 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-06 | Complete | 2025-12-24 | Complete |  | Complete | 2025-12-02 | Open
25 | https://github.com/features/copilot/tutorials | Get started in Visual Studio - Lesson 2: Mastering the basics | 2025-11-17 | 15 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-07 | Complete | 2025-12-29 | Complete |  | Complete | 2025-12-02 | Open
26 | https://github.com/features/copilot/tutorials | Get started in Visual Studio - Lesson 3: Best practices for success | 2025-11-17 | 15 minutes | 2025-11-21 | Open |  | Complete | 2026-01-11 | Complete | 2026-01-09 | Complete | 2026-01-07 | Complete | 2025-12-29 | Complete |  | Complete | 2025-12-02 | Open
27 | Project - 1 | Project 1: Create a simple chatbot that will talk to a LLM and then give you answers. You can use Gemini model. Gemini API key is free to use. Build a UI with any framework of your choice. Build a backend using Python (Langchain framework). | 2025-11-24 | 2 | 2025-11-26 | Open |  | Complete | 2026-01-12 | In-Progress |  | Complete | 2026-01-20 | Complete | 2026-01-02 | Complete | 2025-12-26 | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Complete
28 | Project - 2 | Project 2: The next step is to add a DB layer. Use Postgresql DB. Store the chats into the DB. Get a login for Amzur employees. After login, load all the chats that has been stored in the DB into the chat window. | 2025-11-27 | 2 | 2025-12-01 | Open |  | Complete | 2026-01-12 | Open |  | Complete | 2026-01-21 | Complete | 2026-01-07 | In-Progress |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Complete
29 | Project - 3 | Project 3: Allow login with google. Allow chat threads to be created/updated/deleted. Auto assign chat thread names for every thread. Load the threads on login. | 2025-12-02 | 2 | 2025-12-04 | Open |  | Complete | 2026-01-15 | Open |  | Complete | 2026-01-22 | Complete | 2026-01-13 | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
30 | Project - 4 | Project 4: Allow every chat to have a memory of 5 prevoious conversations. That is, the chat should remember the previous 5 conversations in the chat before answering | 2025-12-05 | 2 | 2025-12-09 | Open |  | Complete | 2026-01-16 | Open |  | Open |  | Complete | 2026-01-19 | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
31 | Project - 5 | Project 5: ALlow the chat window to input images, videos. tables, formulas, code as attachments | 2025-12-10 | 2 | 2025-12-12 | Open |  | Complete | 2026-01-16 | Open |  | Open |  | In-Progress |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
32 | Project - 6 | Project 6: Allow the chat to create images. Use Google gemini 2.0 Image Generation model | 2025-12-15 | 2 | 2025-12-17 | Open |  | Complete | 2026-01-18 | Open |  | Open |  | In-Progress |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
33 | Project - 7 | Project 7: Upload a file into the chat and chat about the file. Lets start with PDF. Use RAG framework. Use ChromaDB for vector storage, OpenAI Embeddings Large for embeddings | 2025-12-18 | 2 | 2025-12-22 | Open |  | Complete | 2026-01-20 | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
34 | Project-8 | Project 8: Connet to a Database and ask questions in natrual language. It could be any questions that typically asked as a SQL statement. | 2025-12-23 | 2 | 2025-12-25 | Open |  | Complete | 2026-01-18 | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
35 | Project 9 | Extend the DB task to include excel file or GSheet and ask questions based on the excel file | 2025-12-26 | 1 | 2025-12-29 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
36 | Project 10 | Have a set of rules and have a set of images. Check if the images are as per rules. This is about data extraction from image and checking against the rules | 2025-12-30 | 2 | 2026-01-01 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
37 | Project 11 | Agents: Understand everything about agents. Learn and create a basic agent based on a LLM using Langchain | 2026-01-02 | 2 | 2026-01-06 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
38 | Project 12 | Agents: Create agent to play a game of tic tac toe using Langchain | 2026-01-07 | 2 | 2026-01-09 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
39 | Project 13 | Agent with MCP example | 2026-01-12 | 2 | 2026-01-14 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
40 | Project 14 | Create agents with N8N | 2026-01-15 | 1 | 2026-01-16 | Open |  | Open |  | Open |  | Open |  | Open |  | Open |  | Complete | https://github.com/amz-ns-sm-sdf/AI-Training-Projects 01-January-2026 | Open
DONE
Formulas:
Assigned Date = WORKDAY([Expected Completion Date, row above],1)
Expected Completion Date = WORKDAY([Assigned Date],[Duration])

## SPOC
Team Member | Team Member Email | Manager Email | ATG SPOC | Required Software Stack
Snehitha Gulla | snehitha.gulla@amzur.com | kameswara.d@amzur.com | Rajesh Talari | Python
Shabana Sheik | shabana.sheik@amzur.com | prerna.kanaujia@amzur.com | Rajesh Talari | Node
Hariprasad Mallipudi | hariprasad.mallipudi@amzur.com | surya.nandarapu@amzur.com | Rajesh Talari | Postgresql or similar database
Shankar Buddha | shankar.buddha@amzur.com | hariprasad.mallipudi@amzur.com | Siva Jamula | VSCode editor
Narasinga Koppu | narasinga.koppu@amzur.com | vijay.mutyala@amzur.com | Siva Jamula | GithubId
Prasad Balaga | prasad.balaga@amzur.com | tarun.dasari@amzur.com | Siva Jamula | GithubCopilot license
Santosh Mudiganti | santosh.mudiganti@amzur.com | vamsi.varri@amzur.com | Geetashish | LLM Api keys for OpenAPI / Google with multimodal feature (Text, Image, etc...)
Kartheek Yandava | kartheek.yandava@amzur.com | vamsi.varri@amzur.com | Geetashish

## Weekly-Connect
Team Member | Team Member Email | ATG SPOC | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-26 | 2026-01-05 | 2026-01-09
General |  |  | 1. Discussed on the overall assignments and projects 2. Covered the software stack required as part of this program | -vscode -github account -github co-pilot -python -node -postgresql or similar | - Updated this tab based on the learning courses progression. - Shankar is on leave toay and could not join the call. - | - Updated this tab based on the learning courses progression. - Shankar is on leave toay and could not join the call. - | - Updated this tab based on the learning courses progression. | - Updated this tab based on the learning courses progression. | - Updated this tab based on the learning courses progression.
Shankar Buddha | shankar.buddha@amzur.com | Siva Jamula | Total online cousers: 26 complete - 9 ¦ In Progress-1 | Total online cousers: 26 complete - 9 ¦ In Progress-1 | Total online cousers: 26 complete - 9 ¦ In Progress-1 | Total online cousers: 26 complete - 9 ¦ In Progress-1 | Total Learning cousers::: 26 Learning Courses::: complete - 12 ¦ Project(s) - Yet To Start | Total Learning cousers::: 26 Learning Courses::: complete - 12 ¦ Project(s) - Yet To Start | Total Learning cousers::: 26 Learning Courses::: complete - 12 ¦ Project(s) - Yet To Start
Narasinga Koppu | narasinga.koppu@amzur.com | Siva Jamula | Total online cousers: 26 complete - 5 ¦ In Progress-0 | Total online cousers: 26 complete - 11 ¦ In Progress - 1 | Total online cousers: 26 complete - 14 ¦ In Progress - 1 ¦ On-Hold-1 | Total online cousers: 26 complete - 21 ¦ In Progress - 1 ¦ On-Hold-3 | Total online cousers: 26 complete - 21 ¦ On-Hold-5 Project(s) - Project-1 Complete, Yet to be reviewed | Total online cousers: 26 complete - 21 ¦ On-Hold-5 Project(s) - Project-1 Complete, Yet to be reviewed | Total online cousers: 26 complete - 21 ¦ On-Hold-5 Project(s) - Project-1, 2 & 3 Complete, Yet to be reviewed
Prasad Balaga | prasad.balaga@amzur.com | Siva Jamula | Total online cousers: 26 complete - 9 ¦ In Progress-2 | Total online cousers: 26 complete - 12 ¦ In Progress - 1 ¦ On-Hold-1 | Total online cousers: 26 complete - 14 ¦ In Progress - 1 ¦ On-Hold-2 | Total online cousers: 26 complete - 25 ¦ In Progress - 0 ¦ On-Hold-1 | Total online cousers: 26 complete - 24 ¦ On-Hold-2 Project(s) - Project-1 Complete, Yet to be reviewed | Total online cousers: 26 complete - 24 ¦ On-Hold-2 Project(s) - Project-1 Complete, Yet to be reviewed | Total online cousers: 26 complete - 24 ¦ On-Hold-2 Project(s) - Project-1 Complete, Project-2 - In ProgressYet to be reviewed

## Task Status (hidden)
Sl No | Project Assignment | Assigned Date | Implementation duration | Expected Completion Date | Naresh Lokanadham |  | Prasad Nunela |  | Ravi Bandaru |  | Revathi Pentakota |  | Santosh Miriyala
[5 empty] | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date | Status | Completion Date
1 | Project 1: Create a simple chatbot that will talk to a LLM and then give you answers. You can use Gemini model. Gemini API key is free to use. Build a UI with any framework of your choice. Build a backend using Python (Langchain framework). Lets see if we can get it ready by Thursday. | 2025-05-05 | 4 days | 2025-05-08 | Complete | 2025-05-08 | In-Progress |  | Complete | 2025-05-08 | Complete | 2025-05-10 | Complete | 2025-05-08
2 | Project 2(May 8th): The next step is to add a DB layer. Use Postgresql DB. Store the chats into the DB. Get a login for Amzur employees. After login, load all the chats that has been stored in the DB into the chat window. Target Date: May 12th | 2025-05-08 | 2 days | 2025-05-12 | Complete | 2025-05-12 | Open |  | Complete | 2025-05-12 | In-Progress |  | Complete | 2025-05-12
3 | Project 3: Allow login with google. Allow chat threads to be created/updated/deleted. Auto assign chat thread names for every thread. Load the threads on login. Target date: May 14th | 2025-05-12 | 3 days | 2025-05-14 | Complete | google auth working AI response working but after google auith integrate unable store data in db 80% completed | Open |  | Complete | Except google auth everything is completed. | Open |  | In-Progress
4 | Project 4: Allow every chat to have a memory of 5 prevoious conversations. That is, the chat should remember the previous 5 conversations in the chat before answering | 2025-05-15 | 2 days | 2025-05-19 | Complete | 2025-05-12 | Open |  | Complete | 2025-05-14 | Open |  | Complete | 16-05-2025
5 | Project 5: ALlow the chat window to show images, videos. tables, formulas, code | 2025-05-20 | 3 days | 2025-05-22 | In-Progress |  |  |  | In-Progress |  |  |  | In-Progress
6 | Project 6: Allow the chat to create images. Use Google gemini 2.0 Image Generation model | 2025-06-04 | 3 days | 2025-06-07
7 | Project 7: Upload a file into the chat and chat about the file. Lets start with PDF. Use RAG framework. Use ChromaDB for vector storage, OpenAI Embeddings Large for embeddings | 2025-06-08 | 4 days | 2025-06-11